## Overview
Archetype – Data Warehouse Rebuild (Phase 1) · Detailed Project Plan & Phase KPIs
Kế hoạch chi tiết & KPI từng giai đoạn · TMA Innovation · Draft for Archetype review
Project start (W1 Monday) · Ngày bắt đầu (thứ 2 tuần 1) | 2026-10-05 | Input – all dates in the plan derive from this cell / Ô nhập – mọi ngày trong kế hoạch tính từ ô này
Contract end · Ngày kết thúc HĐ | 2027-04-09 | Per contract (as updated) / Theo hợp đồng
Warranty end · Kết thúc bảo hành | 2027-07-06 | 3 months after contract end / 3 tháng sau kết thúc HĐ
Plan version · Phiên bản | v0.1 – 08/10/2026 | To be approved by Group IT/IS Director (target W3) / Chờ phê duyệt (mục tiêu W3)
Phase summary · Tổng hợp giai đoạn
Phase · Giai đoạn | Name · Tên | Start wk | End wk | Start date | End date | Milestone | % Complete (avg of tasks)
P1 | Consult, analyze, design & platform setup · Tư vấn, phân tích, thiết kế & dựng nền tảng | 1 | 5 | 2026-10-05 | 2026-11-06 | M1 – Platform baseline (W5) | 0%
P2 | Timesheet E2E · Luồng Timesheet đầu-cuối | 5 | 6 | 2026-11-02 | 2026-11-13 | M2 – Timesheet E2E (W6) | 0%
P3 | Guided build-out & parallel run · Nhân rộng có hướng dẫn & chạy song song | 7 | 13 | 2026-11-16 | 2027-01-01 | M3 – Dashboards & pipelines accepted (W13) | 0%
P4 | pgvector use case, handover & go-live · PoC pgvector, bàn giao & go-live | 13 | 14 | 2026-12-28 | 2027-01-08 | M4 – Phase 1 delivery accepted (W14) | 0%
P5 | Hypercare · Hỗ trợ sau go-live | 15 | 24 | 2027-01-11 | 2027-03-19 | M5 – Hypercare closed (W24) | 0%
How to use · Cách sử dụng
• Yellow cells are inputs: project start date, task Status and % Complete. Ô vàng là ô nhập: ngày bắt đầu, Status và % hoàn thành.
• Start/End week drive the dates and the Gantt bars automatically. Tuần bắt đầu/kết thúc tự sinh ngày và thanh Gantt.
• Each milestone must be accepted (signed minutes) before the next phase starts (contract Art. 8.6). Mỗi mốc phải được nghiệm thu trước khi sang giai đoạn sau (Điều 8.6 HĐ).
• Dates are calendar weeks; public holidays (01/01/2027, Lunar New Year ~06/02/2027) are not deducted – the contract extends the term accordingly. Ngày tính theo tuần lịch, chưa trừ lễ Tết; HĐ cho phép gia hạn tương ứng.
• KPI targets marked "TBC with SME" need confirmation from Archetype data owners during W1–W3. KPI ghi "TBC with SME" cần SME Archetype xác nhận trong W1–W3.
Formulas:
Start date = B4+7*([Start wk]-1)
End date = B4+7*([End wk]-1)+4
Note on B4: Contract start per latest contract update (05/10/2026). Change here to shift every date.

## WBS
Work Breakdown Structure & Timeline · Cấu trúc công việc & tiến độ
Owner/Support: TMA = TMA team · ARC = Archetype · DIR = Group IT/IS Director · BI = Archetype BI · DEV = Archetype DevOps · SME = data owners. Yellow = input.
ID | Phase | Type | Task (EN) | Công việc (VI) | Owner | Support | Start wk | End wk | Start date | End date | Deliverable / Output · Kết quả | Status | % Complete | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24
[14 empty] | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15
P1 | P1 | Phase | Consult, analyze, design & platform setup | Tư vấn, phân tích, thiết kế & dựng nền tảng | TMA | ARC | 1 | 5 | 2026-10-05 | 2026-11-06 | Platform baseline | Not started | 0%
1.1 | P1 | Task | Kick-off; confirm team, RACI, communication & tools | Kick-off; chốt nhân sự, RACI, kênh trao đổi & công cụ | TMA | ARC | 1 | 1 | 2026-10-05 | 2026-10-09 | Kick-off deck, minutes | Not started | 0%
1.2 | P1 | Task | Provide inputs: Azure access, service accounts, SSIS packages, PBIX, table inventory, sample data | Cung cấp đầu vào: quyền Azure, service account, SSIS, PBIX, danh sách bảng, sample data | ARC | TMA | 1 | 1 | 2026-10-05 | 2026-10-09 | Input checklist completed | Not started | 0%
1.3 | P1 | Task | Hand over full Timesheet dashboard requirements | Bàn giao đầy đủ yêu cầu dashboard Timesheet | BI | TMA | 1 | 1 | 2026-10-05 | 2026-10-09 | Timesheet requirement spec | Not started | 0%
1.4 | P1 | Task | Detailed project plan & phase KPIs – draft, review, approve | Kế hoạch chi tiết & KPI giai đoạn – soạn, review, phê duyệt | TMA | DIR | 1 | 3 | 2026-10-05 | 2026-10-23 | Approved plan (this workbook) | Not started | 0%
1.5 | P1 | Task | Current-state assessment: sources, SSIS logic, 5 dashboards, table prioritization | Khảo sát hiện trạng: nguồn, logic SSIS, 5 dashboard, ưu tiên bảng | TMA | BI, SME | 1 | 2 | 2026-10-05 | 2026-10-16 | Assessment report, prioritized table list | Not started | 0%
1.6 | P1 | Task | Legacy connector PoC: SQL Server 2008 TLS/driver via Self-hosted IR | PoC kết nối SQL Server 2008 (TLS/driver) qua Self-hosted IR | TMA | DEV | 2 | 2 | 2026-10-12 | 2026-10-16 | PoC result; CR if limits found | Not started | 0%
1.7 | P1 | Task | Confirm open items: history scope, NAV table count, integration directions | Chốt vấn đề mở: phạm vi lịch sử, số bảng NAV, hướng 4 tích hợp | ARC | TMA | 1 | 2 | 2026-10-05 | 2026-10-16 | Decision log | Not started | 0%
1.8 | P1 | Task | Provision Azure Dev/UAT/Prod: PostgreSQL, Blob, ADF, Container Apps, Key Vault, Monitor, VPN, Windows VM (SHIR) | Dựng Azure Dev/UAT/Prod: PostgreSQL, Blob, ADF, Container Apps, Key Vault, Monitor, VPN, Windows VM (SHIR) | DEV | TMA | 2 | 3 | 2026-10-12 | 2026-10-23 | 3 environments ready | Not started | 0%
1.9 | P1 | Task | HLA/LLD: architecture, data model (layers, naming, conformed dims), security & operations design | HLA/LLD: kiến trúc, data model (lớp, quy ước, dim dùng chung), bảo mật & vận hành | TMA | DEV, BI | 2 | 4 | 2026-10-12 | 2026-10-30 | HLA/LLD document (approved) | Not started | 0%
1.10 | P1 | Task | Platform baseline: parameterized ADF ingestion (watermark, retry, alert), dbt project, Elementary, Git, CI | Nền tảng cơ sở: ADF tham số hóa (watermark, retry, cảnh báo), dbt, Elementary, Git, CI | TMA | DEV | 3 | 5 | 2026-10-19 | 2026-11-06 | Running framework in Dev/UAT | Not started | 0%
1.11 | P1 | Task | Security baseline: Entra ID SSO, RLS framework, masking views, Key Vault secrets | Bảo mật nền: SSO Entra ID, khung RLS, view masking, secrets Key Vault | TMA | DEV | 4 | 5 | 2026-10-26 | 2026-11-06 | Security test cases passed | Not started | 0%
1.12 | P1 | Task | Training #1: platform, ADF & dbt fundamentals (workshop) | Đào tạo #1: nền tảng, ADF & dbt cơ bản (workshop) | TMA | BI, DEV | 5 | 5 | 2026-11-02 | 2026-11-06 | Training material, attendance | Not started | 0%
M1 | P1 | Milestone | M1 – Platform baseline accepted | M1 – Nghiệm thu nền tảng cơ sở | DIR | TMA | 5 | 5 | 2026-11-02 | 2026-11-06 | Signed acceptance minutes | Not started | 0%
P2 | P2 | Phase | Timesheet E2E | Luồng Timesheet đầu-cuối | TMA | BI | 5 | 6 | 2026-11-02 | 2026-11-13 | Reference pipeline | Not started | 0%
2.1 | P2 | Task | Ingest Timesheet sources (≤ 10 tables) into RAW | Nạp nguồn Timesheet (≤ 10 bảng) vào RAW | TMA | DEV | 5 | 5 | 2026-11-02 | 2026-11-06 | RAW tables loaded hourly | Not started | 0%
2.2 | P2 | Task | dbt models staging → dwh → mart (≤ 20 models), Timesheet fact & selected dims | dbt model staging → dwh → mart (≤ 20 model), fact Timesheet & dim chọn lọc | TMA | SME | 5 | 6 | 2026-11-02 | 2026-11-13 | Timesheet mart | Not started | 0%
2.3 | P2 | Task | Elementary tests & reconciliation vs. legacy (≤ 6 acceptance KPIs) | Test Elementary & đối soát với hệ thống cũ (≤ 6 KPI nghiệm thu) | TMA | BI, SME | 6 | 6 | 2026-11-09 | 2026-11-13 | Reconciliation report | Not started | 0%
2.4 | P2 | Task | Build Timesheet dashboard on MART | Xây dashboard Timesheet trên MART | BI | TMA | 5 | 6 | 2026-11-02 | 2026-11-13 | Timesheet dashboard | Not started | 0%
2.5 | P2 | Task | Training #2: pair-working walkthrough of the reference pipeline | Đào tạo #2: pair-working trên pipeline mẫu | TMA | BI | 6 | 6 | 2026-11-09 | 2026-11-13 | Reference pipeline guide | Not started | 0%
M2 | P2 | Milestone | M2 – Timesheet E2E accepted | M2 – Nghiệm thu luồng Timesheet | DIR | TMA | 6 | 6 | 2026-11-09 | 2026-11-13 | Signed acceptance minutes | Not started | 0%
P3 | P3 | Phase | Guided build-out & parallel run | Nhân rộng có hướng dẫn & chạy song song | BI | TMA | 7 | 13 | 2026-11-16 | 2027-01-01 | 6–7 pipelines, 4 integrations | Not started | 0%
3.1 | P3 | Task | Prioritize & plan remaining 5–6 pipelines/dashboards | Ưu tiên & lập kế hoạch 5–6 pipeline/dashboard còn lại | BI | TMA, DIR | 7 | 7 | 2026-11-16 | 2026-11-20 | Build-out backlog | Not started | 0%
3.2 | P3 | Task | Finance pipeline & dashboard | Pipeline & dashboard Finance | BI | TMA | 7 | 9 | 2026-11-16 | 2026-12-04 | Finance mart & dashboard | Not started | 0%
3.3 | P3 | Task | Contract (Project) pipeline & dashboard | Pipeline & dashboard Contract (Project) | BI | TMA | 8 | 10 | 2026-11-23 | 2026-12-11 | Contract mart & dashboard | Not started | 0%
3.4 | P3 | Task | HR pipeline & dashboard | Pipeline & dashboard HR | BI | TMA | 9 | 11 | 2026-11-30 | 2026-12-18 | HR mart & dashboard | Not started | 0%
3.5 | P3 | Task | MD (Managing Director) pipeline & dashboard | Pipeline & dashboard MD | BI | TMA | 10 | 12 | 2026-12-07 | 2026-12-25 | MD mart & dashboard | Not started | 0%
3.6 | P3 | Task | Additional pipeline(s) to reach 6–7 in total | Pipeline bổ sung để đủ 6–7 | BI | TMA | 11 | 13 | 2026-12-14 | 2027-01-01 | Additional mart(s) | Not started | 0%
3.7 | P3 | Task | Rebuild 4 integrations (Timesheet, Budget, Contract, Employee) in ADF | Viết lại 4 tích hợp (Timesheet, Budget, Contract, Employee) bằng ADF | TMA | DEV, SME | 7 | 12 | 2026-11-16 | 2026-12-25 | 4 integration pipelines | Not started | 0%
3.8 | P3 | Task | Historical data load (scope as agreed in 1.7) | Nạp dữ liệu lịch sử (phạm vi theo 1.7) | TMA | DEV | 7 | 10 | 2026-11-16 | 2026-12-11 | History loaded & reconciled | Not started | 0%
3.9 | P3 | Task | Parallel run & reconciliation: legacy vs. new DWH | Chạy song song & đối soát DWH cũ vs. mới | BI | TMA, SME | 7 | 13 | 2026-11-16 | 2027-01-01 | Weekly reconciliation report | Not started | 0%
3.10 | P3 | Task | Weekly pair-working clinics & code reviews | Buổi pair-working & review code hằng tuần | TMA | BI | 7 | 13 | 2026-11-16 | 2027-01-01 | Review log | Not started | 0%
3.11 | P3 | Task | UAT by Finance & Accounting and HR | UAT bởi Finance & Accounting và HR | SME | BI, TMA | 11 | 13 | 2026-12-14 | 2027-01-01 | UAT sign-off, defect log | Not started | 0%
M3 | P3 | Milestone | M3 – Pipelines/dashboards accepted; go/no-go for decommission | M3 – Nghiệm thu pipeline/dashboard; quyết định ngưng DWH cũ | DIR | TMA, BI | 13 | 13 | 2026-12-28 | 2027-01-01 | Signed acceptance minutes | Not started | 0%
P4 | P4 | Phase | pgvector use case, handover & go-live | PoC pgvector, bàn giao & go-live | TMA | ARC | 13 | 14 | 2026-12-28 | 2027-01-08 | Phase 1 delivery | Not started | 0%
4.1 | P4 | Task | pgvector + text-to-SQL PoC: metadata embeddings, LLM, guardrails, Metabase integration | PoC pgvector + text-to-SQL: embedding metadata, LLM, guardrail, tích hợp Metabase | TMA | BI | 13 | 14 | 2026-12-28 | 2027-01-08 | Working PoC + test question set | Not started | 0%
4.2 | P4 | Task | Vulnerability scan & remediation | Quét lỗ hổng & khắc phục | DEV | TMA | 13 | 14 | 2026-12-28 | 2027-01-08 | Scan report, 0 critical/high | Not started | 0%
4.3 | P4 | Task | Handover documents (bilingual): technical doc, source code, test results, user guide, install guide | Tài liệu bàn giao (song ngữ): kỹ thuật, mã nguồn, kiểm thử, HDSD, cài đặt | TMA | — | 13 | 14 | 2026-12-28 | 2027-01-08 | 5 deliverables | Not started | 0%
4.4 | P4 | Task | Training #3: operations runbook (monitoring, incidents, backup/restore) | Đào tạo #3: runbook vận hành (giám sát, sự cố, backup/restore) | TMA | DEV, BI | 14 | 14 | 2027-01-04 | 2027-01-08 | Runbook, attendance | Not started | 0%
4.5 | P4 | Task | Go-live & decommission legacy DWH | Go-live & ngưng DWH cũ | DEV | TMA, BI | 14 | 14 | 2027-01-04 | 2027-01-08 | Legacy DWH stopped | Not started | 0%
M4 | P4 | Milestone | M4 – Phase 1 delivery accepted | M4 – Nghiệm thu bàn giao Phase 1 | DIR | TMA | 14 | 14 | 2027-01-04 | 2027-01-08 | Signed acceptance minutes | Not started | 0%
P5 | P5 | Phase | Hypercare | Hỗ trợ sau go-live | TMA | DEV, BI | 15 | 24 | 2027-01-11 | 2027-03-19 | Stable operations | Not started | 0%
5.1 | P5 | Task | Hypercare: issue triage, defect fixes, performance tuning | Hypercare: phân loại sự cố, sửa lỗi, tối ưu hiệu năng | TMA | DEV, BI | 15 | 24 | 2027-01-11 | 2027-03-19 | Incident log | Not started | 0%
5.2 | P5 | Task | Daily 1-hour sync or weekly review | Họp 1 giờ hằng ngày hoặc review hằng tuần | TMA | DEV, BI | 15 | 24 | 2027-01-11 | 2027-03-19 | Meeting notes | Not started | 0%
5.3 | P5 | Task | Backup/restore tests against RPO/RTO | Kiểm thử backup/restore theo RPO/RTO | DEV | TMA | 16 | 16 | 2027-01-18 | 2027-01-22 | Restore test report | Not started | 0%
5.4 | P5 | Task | Second restore test & monthly operations review | Restore test lần 2 & review vận hành hằng tháng | DEV | TMA | 22 | 22 | 2027-03-01 | 2027-03-05 | Ops review report | Not started | 0%
5.5 | P5 | Task | Internal team ships ≥ 1 new pipeline/report independently | Đội nội bộ tự triển khai ≥ 1 pipeline/báo cáo mới | BI | TMA | 17 | 23 | 2027-01-25 | 2027-03-12 | New pipeline in Prod | Not started | 0%
M5 | P5 | Milestone | M5 – Hypercare closed; final acceptance | M5 – Kết thúc hypercare; nghiệm thu cuối | DIR | TMA | 24 | 24 | 2027-03-15 | 2027-03-19 | Final acceptance minutes | Not started | 0%
X | X | Phase | Cross-cutting governance | Quản trị xuyên suốt | TMA | ARC | 1 | 24 | 2026-10-05 | 2027-03-19 |  | Not started | 0%
X.1 | X | Task | Weekly meeting (60 min), weekly status report & RAID log | Họp tuần (60 phút), báo cáo tuần & RAID log | TMA | ARC | 1 | 24 | 2026-10-05 | 2027-03-19 | Weekly report | Not started | 0%
X.2 | X | Task | Daily scrum (30 min, internal TMA) & daily update | Daily scrum (30 phút, nội bộ TMA) & cập nhật hằng ngày | TMA | — | 1 | 14 | 2026-10-05 | 2027-01-08 | Daily update | Not started | 0%
Gantt legend · Chú thích: dark blue = phase · blue = task · orange = milestone · green = task done
Formulas:
Start date = Overview!$B4+7*([Start wk]-1)
End date = Overview!$B4+7*([End wk]-1)+4

## Phase KPIs
Phase KPIs & acceptance criteria · KPI & tiêu chí nghiệm thu từng giai đoạn
Targets marked "TBC with SME" to be confirmed by Archetype data owners in W1–W3. Actual & Met? are filled at each milestone review.
Phase | KPI (EN) | KPI (VI) | Target · Mục tiêu | Measurement · Cách đo | Evidence · Bằng chứng | Owner | Due wk | Actual · Thực tế | Met? (Y/N)
P1 | Detailed plan & phase KPIs approved | Kế hoạch & KPI được phê duyệt | Signed by W3 (21/10/2026) | Approval email / minutes | Approved workbook | TMA / DIR | 3
P1 | Project inputs received | Đầu vào dự án đã nhận | ≥ 90% of input checklist by end of W1; 100% by W2 | Checklist completion | Input checklist | ARC | 2
P1 | Source connectivity (legacy connector PoC) | Kết nối nguồn (PoC legacy) | 100% sources reachable via SHIR: 15 NAV DBs, MySQL, PostgreSQL 18, files | Test extraction per source | PoC report | TMA / DEV | 2
P1 | Environments provisioned | Môi trường đã dựng | Dev, UAT, Prod ready (3/3) | Environment checklist | Azure resource inventory | DEV | 3
P1 | HLA/LLD approved | HLA/LLD được phê duyệt | Approved by W4 | Review sign-off | HLA/LLD document | TMA / DIR | 4
P1 | Platform baseline stability | Độ ổn định nền tảng | Sample hourly pipeline ≥ 95% successful runs over 5 consecutive working days | ADF run history | Azure Monitor export | TMA | 5
P1 | Security baseline | Bảo mật nền | 100% RLS & masking test cases passed; SSO working | Security test cases | Test results | TMA | 5
P2 | Timesheet E2E delivered | Hoàn thành luồng Timesheet | Live in UAT/Prod by end of W6 | Milestone review | Demo + acceptance minutes | TMA / BI | 6
P2 | Data freshness | Độ trễ dữ liệu | ≤ 60 min from source change to MART | Load timestamps vs. source | Freshness test (Elementary) | TMA | 6
P2 | Reconciliation vs. legacy | Đối soát với hệ thống cũ | 100% of ≤ 6 acceptance KPIs within agreed tolerance (TBC with SME) | KPI comparison legacy vs. new | Reconciliation report | BI / SME | 6
P2 | Data quality tests | Kiểm thử chất lượng dữ liệu | 100% critical Elementary tests passing | Elementary report | DQ report | TMA | 6
P2 | Dashboard performance | Hiệu năng dashboard | Timesheet dashboard opens ≤ 30 s | Timed load test | Test log | BI | 6
P3 | Pipelines in production | Số pipeline vận hành | 6–7 pipelines incl. Timesheet | Pipeline inventory | dbt/ADF repository | BI / TMA | 13
P3 | Pipeline reliability | Độ tin cậy pipeline | ≥ 98% successful runs per week (after retries) | ADF run history | Weekly report | TMA / BI | 13
P3 | Parallel-run reconciliation | Đối soát chạy song song | 5 legacy dashboards: 100% KPIs within tolerance for ≥ 2 consecutive weeks | Weekly reconciliation | Reconciliation reports | BI / SME | 13
P3 | Integrations replaced | Thay thế tích hợp | 4/4 integrations running on agreed schedule, 0 open critical defects | Integration run log | Run log + defect log | TMA | 12
P3 | Historical data | Dữ liệu lịch sử | 100% of agreed history scope loaded & reconciled (row counts) | Row-count comparison | History load report | TMA | 10
P3 | Internal enablement | Năng lực nội bộ | Archetype BI builds ≥ 4 of 5–6 pipelines with TMA guidance | Commit history / reviews | Git log | BI | 13
P3 | UAT quality | Chất lượng UAT | 0 open critical/high defects; feedback within 1 week | Defect log | UAT sign-off | SME | 13
P4 | pgvector / text-to-SQL PoC | PoC pgvector / text-to-SQL | ≥ 70% correct SQL on a 20-question test set (TBC); 100% read-only & RLS-respected | Test question set | PoC test report | TMA | 14
P4 | Security scan | Quét bảo mật | 0 open critical/high vulnerabilities | Vulnerability scan | Scan report | DEV / TMA | 14
P4 | Handover documents | Tài liệu bàn giao | 5/5 deliverables delivered (bilingual) | Deliverable checklist | Handover minutes | TMA | 14
P4 | Legacy DWH decommissioned | Ngưng DWH cũ | Stopped in W14 after M3 go decision | Change record | Decommission record | DEV | 14
P4 | Operations readiness | Sẵn sàng vận hành | Runbook delivered; DevOps & BI trained (100% attendance of named staff) | Training records | Attendance + runbook | TMA | 14
P5 | Response time | Thời gian phản hồi | 100% of requests responded within 2 working days | Ticket timestamps | Incident log | TMA | 24
P5 | Recovery objectives | Mục tiêu khôi phục | Restore tests meet RPO 1 business day / RTO 4 h | Restore test | Restore test reports | DEV | 22
P5 | Operational stability | Vận hành ổn định | ≥ 98% pipeline success & ≥ 95% hours fresh ≤ 60 min (monthly) | ADF + Elementary | Monthly ops review | TMA / DEV | 24
P5 | Self-sufficiency | Tự chủ vận hành | ≥ 1 new pipeline/report shipped by Archetype team independently | Git / release log | Release record | BI | 23
P5 | Final acceptance | Nghiệm thu cuối | Signed by end of W24 | Acceptance minutes | Final acceptance minutes | DIR | 24
KPI scorecard · Tổng hợp
Phase | # KPIs | # Met (Y) | % Met
P1 | 7 | 0 | 0%
P2 | 5 | 0 | 0%
P3 | 7 | 0 | 0%
P4 | 5 | 0 | 0%
P5 | 5 | 0 | 0%

## Milestones
Milestones & acceptance · Mốc & nghiệm thu
Each milestone must be accepted before moving to the next stage (contract Art. 8.6). Client feedback within 15 working days of handover notice (Art. 8.2).
ID | Milestone (EN) | Mốc (VI) | Week | Target date | Acceptance criteria · Tiêu chí | Sign-off | Status | Actual date
M0 | Kick-off & contract start | Kick-off & bắt đầu hợp đồng | 1 | 2026-10-09 | Kick-off held; payment milestone 1 (50%) invoiced | TMA / DIR | Planned
M1 | Platform baseline | Nền tảng cơ sở | 5 | 2026-11-06 | All P1 KPIs met (Phase KPIs sheet) | DIR | Planned
M2 | Timesheet E2E | Luồng Timesheet đầu-cuối | 6 | 2026-11-13 | All P2 KPIs met | DIR | Planned
M3 | Pipelines/dashboards accepted; go/no-go for decommission | Nghiệm thu pipeline/dashboard; quyết định ngưng DWH cũ | 13 | 2027-01-01 | All P3 KPIs met; UAT signed | DIR | Planned
M4 | Phase 1 delivery accepted (go-live) | Nghiệm thu bàn giao Phase 1 (go-live) | 14 | 2027-01-08 | All P4 KPIs met; 5 deliverables handed over | DIR | Planned
M5 | Hypercare closed; final acceptance | Kết thúc hypercare; nghiệm thu cuối | 24 | 2027-03-19 | All P5 KPIs met | DIR | Planned
W | Warranty end | Kết thúc bảo hành | — | 2027-07-06 | Defects in scope fixed free of charge until this date | DIR | Planned
PAY2 | Payment milestone 2 (50%) | Thanh toán đợt 2 (50%) | — | 2027-08-05 | Within 30 days after final acceptance & warranty completion record (Art. 10) | DIR | Planned
Formulas:
Target date = Overview!$B4+7*([Week]-1)+4
Note on E8: 01/01/2027 is a public holiday – hold the M3 review on Thu 31/12/2026 or Mon 04/01/2027.
Note on E12: Indicative: 30 days after warranty end; actual date depends on receipt of complete payment dossier.

## RAID
RAID log · Rủi ro, Giả định, Vấn đề, Phụ thuộc
R = Risk (rủi ro) · A = Assumption (giả định) · I = Issue (vấn đề) · D = Dependency (phụ thuộc). Updated weekly with the status report.
ID | Type | Description (EN) | Mô tả (VI) | Impact | Likelihood | Mitigation / Action | Owner | Due wk | Status
R1 | Risk | SQL Server 2008 TLS/driver incompatible with Self-hosted IR | SQL Server 2008 không tương thích TLS/driver với SHIR | High | Medium | PoC in W2; fallback driver/TLS settings; CR if limits remain | TMA | 2 | Open
R2 | Risk | Master data (entity, office, country) not standardized until 11/2026 | Master data chưa chuẩn hóa xong đến 11/2026 | High | High | Use mapping tables & default codes; reprocess once finalized | SME | 8 | Open
R3 | Risk | Historical load scope unclear (full history vs. 2 years); Timesheet 1.5M rows | Phạm vi dữ liệu lịch sử chưa rõ; Timesheet 1.5 triệu dòng | Medium | Medium | Decide in 1.7; partition & summarize older years | ARC | 2 | Open
R4 | Risk | SME availability for KPI/mapping confirmation | SME không kịp xác nhận KPI/mapping | High | Medium | 2-working-day response rule; escalate to Director | DIR | 24 | Open
R5 | Risk | Archetype BI ramp-up on dbt/ADF slower than planned | Đội BI làm quen dbt/ADF chậm hơn kế hoạch | Medium | Medium | Training #1–#2, weekly clinics, reference pipeline | TMA | 13 | Open
A1 | Assumption | Archetype provisions Azure services, VPN and Windows VM by W3 | Archetype cấp dịch vụ Azure, VPN, Windows VM trước W3 | High | — | Track in 1.8 | DEV | 3 | Open
A2 | Assumption | DWH is read-only; hourly batch, no CDC in Phase 1 | DWH chỉ đọc; batch theo giờ, không CDC | Medium | — | Confirmed in contract assumptions | TMA | 1 | Closed
D1 | Dependency | Timesheet requirements from Archetype BI in W1 | Yêu cầu Timesheet từ BI Archetype trong W1 | High | — | Blocks P2 start | BI | 1 | Open
D2 | Dependency | Contract wording update for tech stack (ADF + dbt, no Airflow/dlt) | Cập nhật câu chữ HĐ về stack (ADF + dbt, bỏ Airflow/dlt) | Medium | — | Contract amendment / appendix | TMA / DIR | 3 | Closed
I1 | Issue | (example) Service account for MySQL not yet created | (ví dụ) Chưa có service account MySQL | Medium | — | Request raised to DevOps | DEV | 2 | Open